## project
Project Planner
Project | Story |  | Story | Task | PERCENT
Stories | Task | Team Member | Points | Hours | COMPLETE
| DB Script | Bijay |  | 8 | 0%
| Design | Mahesh |  | 8 | 0%
| DAO Layer | Seema |  | 4 | 0%
1.Register a Customer | Service Layer | Seema |  | 16 | 0%
| Unit Testing | Seema |  | 6 | 0%
| Rest WS | Mahesh |  | 6 | 0%
| Unit Test Case | Mahesh |  | 4 | 0%
| SOAP WSDL | Bijay |  | 8
| SOAP WebService | Bijay |  | 6 | 0%
| Unit Testing | Bijay |  | 8
| Address Verification | Mahesh |  | 16
| Integration Testing | Subhashish |  | 8
|  | Total |  | 98
Data Setup
| DB Script | Rabie |  | 8
| Product Data Set UP Entry(20) | Rabie |  | 8
| Customer Data Set UP Entry(10) | Rabie |  | 4
| Order Data Set UP Entry(20) | Rabie |  | 8 | 0%
| Entities for Tables | Rabie |  | 8 | 0%
| Design | Jaffar |  | 16
| DAO Layer(QUERIES) | Rabie |  | 6 | 0%
2. Search Customer | Service Layer | Rabie |  | 8 | 0%
| Unit Testing | Rabie |  | 4 | 0%
| Rest WS | Jaffar |  | 4 | 0%
| Unit Test Case | Jaffar |  | 2
| SOAP WSDL | Jaffar |  | 8
| SOAP WebService | Jaffar |  | 4
| Unit Testing | Jaffar |  | 2
| Integration Testing | Rabie |  | 8
|  | Total |  | 98
| DB Script | Shubhasish |  | 8 | 0%
| Design |  |  |  | 0%
| Class Diagram | Shreekit |  | 8
| Sequence Diagram | Seema |  | 8
| DAO Layer | Bijay |  | 16 | 0%
3.Case Registration | Service Layer | Shreekit |  | 24 | 0%
| Unit Testing | Shreekit |  | 8 | 0%
| Rest WS | Seema |  | 8 | 0%
| Unit Test Case | Seema |  | 4
| SOAP WSDL | Balram |  | 8
| SOAP WebService | Balram |  | 8
| Unit Testing | Balram |  | 4
| Integration Testing | Shubhashish |  | 8
|  | Total |  | 112
| Project Setup | Shubhashais |  | 16 | 0%
4.Project Setup